## Slide 1: Enabling an adaptive MEL culture in fragile and conflict-affected contexts
Lessons from the CSSF Global MEL project
September 2021

## Slide 2
May 2021

## Slide 3
Agenda
What unique challenges does CSSF pose when developing a MEL system?
How has the thinking of adaptive MEL been applied to this context?
How does a culture of adaptation scale from programmes to a diverse geographic and thematic fund?
www.integrityglobal.com | 3
Enabling an adaptive MEL culture in fragile and conflict-affected contexts
Lessons from the CSSF Global MEL project

## Slide 4
What unique challenges does CSSF pose when developing a MEL system?
How has the thinking of adaptive MEL been applied to this context?
How does a culture of adaptation scale from programmes to a diverse geographic and thematic fund?
www.integrityglobal.com | 4
Enabling an adaptive MEL culture in fragile and conflict-affected contexts
Lessons from the CSSF Global MEL project

## Slide 5: Background: What is the CSSF?
The Conflict, Stability and Security Fund (CSSF) is a unique cross-government fund created in to prevent conflicts and tackle threats to UK interests that arise from instability
£1.26 billion fund delivers 90 programmes in 70 countries
Split between ODA and non-ODA funding
Cross-departmental integrated delivery with devolved responsibility
Unique operating structure from fund - portfolio – programme - project levels
Enabling an adaptive MEL culture in fragile and conflict-affected contexts
Lessons from the CSSF Global MEL project

## Slide 6: How are CSSF programmes unique?
SOMALIA SSR
Working with government to provide strategic direction for Somali security sector development
Coordinating security across federal member states and AMISOM
Integrated delivery across departments (FCO, MOD, DFID)
Working across fragile political settlements
Flexible deployment of resources to address new or unanticipated events
High level of risk
Enabling an adaptive MEL culture in fragile and conflict-affected contexts
Lessons from the CSSF Global MEL project
www.integrityglobal.com | 6
Notes: On-the-ground realities of CSSF programmes differ significantly from other types of donor-funded programmes

## Slide 7: Addressing complexity within CSSF
Operating with limited information or unreliable evidence sources
Drivers of conflict or instability are constantly changing and evolving
Overlapping systems of delivery
High-risk, experimental, or pilot interventions
Politicised environments and objectives
Short-term timelines with need for quick successes
Catalytic nature of change
Enabling an adaptive MEL culture in fragile and conflict-affected contexts
Lessons from the CSSF Global MEL project

## Slide 8
What unique challenges does CSSF pose when developing a MEL system?
How has the thinking of adaptive MEL been applied to this context?
How does a culture of adaptation scale from programmes to a diverse geographic and thematic fund?
www.integrityglobal.com | 8
Enabling an adaptive MEL culture in fragile and conflict-affected contexts
Lessons from the CSSF Global MEL project

## Slide 9: What is GMEL?
Contracted to support the development of a stronger, more agile, and sustainable ecosystem for MEL
Designed with overarching aim of bringing the CSSF to a level of evaluability
Develop the systems and capabilities necessary to synthesise results, evidence, and learning across the Fund
Enabling an adaptive MEL culture in fragile and conflict-affected contexts
Lessons from the CSSF Global MEL project

## Slide 10: GMEL’s approach to adaptive MEL
Creating an ongoing link between evidence and adaptation
Embraces complexity, uncertainty, external influences, and changing contexts
Uses evaluative thinking to create feedback loops between evidence, context, learning, and decision-making
Involves addressing a change in mindset by addressing adaptation as a cultural challenge
Enabling an adaptive MEL culture in fragile and conflict-affected contexts
Lessons from the CSSF Global MEL project
Evaluative thinking reflects the ability to creatively navigate uncertainty, ambiguity, and complexity
Hills
“
”

## Slide 11: Targeted Adaptive MEL interventions
Enabling an adaptive MEL culture in fragile and conflict-affected contexts
Lessons from the CSSF Global MEL project
DESIGN
Developing an actor-based theory of change
Alternatives to results frameworks using outcome mapping/harvesting
Ensuring conflict sensitive results and evidence measures
DELIVERY
Improving use of context monitoring
Incorporating real time data collection dashboards
Participatory methods to collect change stories or harvest outcomes
GOVERNANCE
Synthesising evidence across thematics or geographies
Improving understanding of risk
Development of fund level framing indicators

## Slide 12: Example: Support to the Cyber Portfolio
The Cyber Portfolio
Addresses Cyber Security challenges at multiple levels using an actor-based theory of change
Enabling an adaptive MEL culture in fragile and conflict-affected contexts
Lessons from the CSSF Global MEL project
KEY OBJECTIVES
Governments better protecting critical national infrastructure from cyber attacks​
Improved cybersecurity attitudes among private citizens and the private sector

## Slide 13: Example: Support to the Cyber Portfolio
Progress Markers
Reflects an actor based change (ABC) theory of change
A form of outcome mapping that uses behaviour change as a means of measuring progress
A set of statements describing a gradual progression of changed behaviour in a boundary partner leading to the ideal outcome challenge​
Graduated indicators focusing on the depth and quality of change
Enabling an adaptive MEL culture in fragile and conflict-affected contexts
Lessons from the CSSF Global MEL project

## Slide 14: Outcome Mapping
Enabling an adaptive MEL culture in fragile and conflict-affected contexts
Lessons from the CSSF Global MEL project
PREDETERMINED OUTCOMES
UNDETERMINED OUTCOMES
LOGFRAME
Conventional indicators that measure progress towards intended results or outcomes
OUTCOME MAPPING (Progress markers)
A set of statements describing a gradual progression of changed behaviour in a boundary partner leading to the ideal outcome challenge
OUTCOME HARVESTING
Collecting evidence of what has changed, then working backwards, determines whether and how an intervention contributed to those changes.

## Slide 15: Progress Markers
Enabling an adaptive MEL culture in fragile and conflict-affected contexts
Lessons from the CSSF Global MEL project
LOVE TO SEE (Deep transformation of behaviour): Private sector actors contribute to the improvement of international cyber security practices
LIKE TO SEE (Active engagement, building support and enrolling others): Private sector actors establishing internal cyber security mechanisms
EXPECT TO SEE (Immediate response such as knowledge acquisition): Private sector actors attending forums on cyber security

## Slide 16: Why is this adaptive?
Focus on the depth and quality of change rather than quantitative measures against targets
Can flex depending on changes in priorities or strategy
Describe the process of change qualitatively
Enables capture of unintended consequences in addition to planned results
Enabling an adaptive MEL culture in fragile and conflict-affected contexts
Lessons from the CSSF Global MEL project

## Slide 17
What unique challenges does CSSF pose when developing a MEL system?
How has the thinking of adaptive MEL been applied to this context?
How does a culture of adaptation scale from programmes to a diverse geographic and thematic fund?
www.integrityglobal.com | 17
Enabling an adaptive MEL culture in fragile and conflict-affected contexts
Lessons from the CSSF Global MEL project

## Slide 18: Challenges of Scale
Programme adaptations do not automatically lead to fund-level culture change
Enabling an adaptive MEL culture in fragile and conflict-affected contexts
Lessons from the CSSF Global MEL project
Time
Cultural Barriers
Resources
Governance and bureaucracy
Data synthesis
Light touch changes

## Slide 19: GMEL’s fund-level theory of change
GMELs theory of change is meant to address the issue of evaluative thinking through an ecosystem approach
Addressing a culture that is not centralised or uniform
Design thinking and complexity awareness are central to GMELs delivery
Enabling an adaptive MEL culture in fragile and conflict-affected contexts
Lessons from the CSSF Global MEL project

## Slide 20: GMEL’s change areas
Enabling an adaptive MEL culture in fragile and conflict-affected contexts
Lessons from the CSSF Global MEL project
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
Sales | 1 | 1 | 1 | 1
Enabling architecture
The CSSF offers and makes it easy for people to draw on a set of tools, frameworks and processes, including evidence synthesis, making good MEL practice attainable and relevant
Convening spaces
The CSSF network convenes and creates opportunities for stakeholders to engage and connect, both within the CSSF and beyond, to enable more learning
Equipping the network
Individuals across the CSSF network have the confidence and skills to make meaningful and systematic contributions to accountability, evidence-based decision making and learning
Offering reassurance
Senior Leadership believes that collective efforts to strengthen MEL practice are important. They need to see that efforts to strengthen the MEL ecosystem help them

## Slide 21: Evaluative thinking at fund-level
Evaluation as a feedback mechanism from evidence to adaptation
Developing a system of evaluability – evaluation as a process
Use of summative and process evaluation as an adaptive tool
Use of data analytics and synthesis
Enabling an adaptive MEL culture in fragile and conflict-affected contexts
Lessons from the CSSF Global MEL project
www.integrityglobal.com | 21

## Slide 22: Scaling adaptation to fund-level
Challenge of going from flexibility – response to a rapidly changing environment, to adaptation – systematically learning from evidence to be effective through complexity
Addressing institutional barriers that prevent adaptation
Aim is to scale ET mindset from programmes to a broad geographic and thematic fund to enable adaptation
Scaling light touch interventions into fund-wide change
Enabling an adaptive MEL culture in fragile and conflict-affected contexts
Lessons from the CSSF Global MEL project
www.integrityglobal.com | 22
Notes: The CSSF is already flexible – it involved rapid deployment, short-term interventions, fast-changing priorities

## Slide 23: Questions?

## Slide 24: Questions for discussion:
How does evaluative thinking scale from on-the-ground projects to portfolios and funds?
What does adaptation mean across a broad geographical and thematic fund?
What tend to be the biggest blockers of cultural change toward evaluative thinking?
What is the relationship between evaluative thinking and adaptive programming?
How does understanding of risk contribute to adaptation or evaluative thinking?